## Functions
Function | Status
Login with google | Done
Login with facebook | Done
Logout | Done
Dating (Automation+ Manual) | Done
Like/Unlike pet | Done
Ignore Pet | Done
Create new user | Done
View user's profile | In Progress | 80% ( pending: list posts)
Update user's profile | Done
View pet's profile | In Progress | 80% (pending: show featured images of pet)
Create new pet | Done
Update pet's profile | Done
Create Post | Pending
Post Screen | Pending
Chatting | In Progress | 80% (fixing styles)
Finding | Pending
Report post | Pending
Web management | In Progress | 70% (pending: review report)
Feedback | Done

## Documents
Docs | Status
Introduction | Done
Software Project Management Plan | Done
Requirements | Done
Detail Design-1 | Done
Detail Design-2 | Done
Testing-1 | Done
Testing-2 | In Progress
User-Manual | Not Started